## Slide 1: Decommissioning San Onofre
Stevie Vaughan
Oversight Manager
Radiation Protection & Waste
October 31, 2019
Low-Level Radioactive Waste Forum

## Slide 2
San Onofre Plant

## Slide 3: Goal & Principles
Complete decommissioning in a safe, timely, transparent, & cost-efficient manner while maintaining high standards of environmental protection
Safety
Engagement
Stewardship

## Slide 4: San Onofre Plant History
Unit 1
Online January 1968
Retired 1992, partially decommissioned
Units 2 and 3
Online November 1983, April 1984
  Retired June 7, 2013
  Spent Fuel Storage
    Over 50 years
    Dry Cask Storage since 2003
4

## Slide 5
SONGS Decommissioning Plan

## Slide 6: Decommissioning Plan Subject to Change
Future milestones are tentative

## Slide 7
Project Milestones

## Slide 8: Milestones 2014 - 2017
  2014
  Submitted Post-Shutdown Decommissioning Activities Report, Decommissioning Cost Estimate, Irradiated Fuel Management Plan to NRC
  Staffing transitions and down sizing
  2015-2017
  Spent Fuel Pool Island
  Cold and Dark
  Construct Independent Spent Fuel Storage Installation (ISFSI) Pad
  Decommissioning General Contractor (DGC) selection and mobilization

## Slide 9: Milestones 2018 - Present
  2018 – Present
ISFSI Only NRC License Amendments
  Technical Specifications
  Emergency Plan
  Security Plan
Obtain Environmental Permits
  Safely transfer used fuel to ISFSI

## Slide 10: California Environmental Quality Act (CEQA)
MILESTONE | TIMING
Final EIR and lease certified by CSLC at public meeting | Approved March 21, 2019
CDP application for onshore work from CCC to be considered at public meeting in San Diego | Approved October 17, 2019
Two state permits required to start decontamination & dismantlement
Offshore work requires a CDP from CCC with a public meeting anticipated mid-2021

## Slide 11: Used Fuel Management

## Slide 12: SONGS Independent Spent Fuel Storage Installation
AREVA System
(50 spent fuel canisters)
Holtec System
(73 spent fuel canisters)

## Slide 13: Spent Fuel Pool “Wet” Storage

## Slide 14: Areva Nuhoms

## Slide 15
Holtec HI-STORM UMAX
Corrosion-Resistant Stainless Steel Multipurpose Canister
Reinforced Concrete Pad (Top/Bottom)
Stainless Steel Lid
Corrosion-Resistant Stainless Steel Cavity Enclosure Container

## Slide 16
EXPANDED ISFSI
Spent Fuel Pools 2668 fuel assemblies
3855 fuel assemblies in 123 canisters
FUTURE STATE
73 canisters (2668 fuel assemblies)
+
existing 50 canisters (1187 fuel assemblies)
INITIAL STATE
16
Existing ISFSI
50 canisters (1187 fuel assemblies)
On-site Used Fuel Storage
CANISTERS ARE BEING LOADED ONTO THE ISFSI

## Slide 17: Used Fuel Transportation Readiness
Some fuel qualified for transport now
Remaining fuel qualifies over time
 | NOW | ‘20 | ‘21 | ‘22 | ‘23 | ‘24 | ‘25 | ‘26 | ‘27 | ‘28 | ‘29 | ‘30 | TOTAL
Units 2/3 AREVA NUHOMS 24PT4 |  |  |  |  |  |  |  |  |  |  |  |  | 
Unit 1 AREVA NUHOMS 24PT1 |  |  |  |  |  |  |  |  |  |  |  |  | 
Units 2/3 HOLTEC MPC-37 |  |  |  |  |  |  |  |  |  |  |  |  | 
6
1
9
5
1
1
67
2
2
33
17
73
33
2

## Slide 18
Decommissioning Cost Estimate

## Slide 19: Decommissioning Cost Estimate
Chart: 
| License Termination | Spent Fuel Management | Site Restoration
Column1 | 2.112 | 1.276 | 1.023
Total estimate = $4.411 Billion (100% share, 2014$$)
Current trust fund balances expected to fully fund decommissioning

## Slide 20: Estimated Waste Types/Amounts (Volumes noted from DCE)
Chart: 
| Class A - 3,648,469 | Class B - 15,199 | Class C - 8,191 | GTCC - 1,882 | Other (Class II Landfill/Scrap Metal) - 36,763,917
Estimated Burial Volumes (CF) | 3648469 | 15199 | 8191 | 1882 | 36763917

## Slide 21: Community Engagement

## Slide 22: San Onofre Community Engagement Panel
Created in 2014 to serve as an open conduit between the public and the utility
Eighteen representatives from surrounding cities and counties, including:
Elected officials and agency representatives | Local law enforcement
Representatives of the U.S. military | Business and labor communities
Local environmental organizations | Local schools and academic institutions

## Slide 23: Visitors
Since 2014, 3000+ visitors including:
The Public - walking tours twice monthly
High school students, teachers and parents
California Energy Commission
Members of Congress: Harley Rouda (D-48), Mike Levin (D-49), Scott Peters (D-52), Katie Porter (D-45); John Shimkus (R-IL)
City Council members from San Clemente, San Juan Capistrano, Dana Point, Encinitas
San Diego Regional Water Quality Board
Native American Tribal Nations
City of San Diego Fire Department
Orange County Coastkeepers
Ocean Institute
San Diego Union Tribune
Sierra Club, Los Angeles and San Diego Chapters
Surfrider Foundation
23

## Slide 24: Public Engagement
Keep the public informed
  Quarterly updates and annual progress reports
  Advance notice of regulated ocean discharges
  More frequent reporting of environmental monitoring program results
  Live-time radiological monitoring for spent fuel storage facility
  Designated liaison as public point of contact
  Website: www.SONGScommunity.com
24

## Slide 25
Framework of Oversight

## Slide 26: Framework of Oversight
A Graded Approach to Oversight:
  Risk weighted, management prioritized, and resourced leveled
Clearly Define Organizational Responsibilities:
  Oversight Specialist complete a qualification guide prior to independent field oversight
  Multiple Desktop Guides created to provide guidance and expectations
Comment Resolution Methodology:
  Predictable methodology for mediating disagreements on the issues
Defined Behaviors and Expectations:
    One voice and one standard
    Promote a healthy relationship with the Contractor
    High quality oversight
    Maintain and protect credibility
    Maintain Independence
    Comments grounded (Compliance based & the 3 R’s)
9 of 35
26
Notes: 3

## Slide 27
Lessons Learned

## Slide 28: Lessons Learned
Regulatory
Open and frequent communication with Region and Headquarters
Maintain close cooperation with other utilities
Do not under estimate amount of time and effort that maybe required for various permits or permitting agencies that may be involved
Contractors
Know vendor’s capabilities (technical rigor, regulatory, PR, etc.)
Know design basis
Take caution in “Turn Key” operations

## Slide 29: Lessons Learned
Community Engagement
Transparent, “plain English”
Community Engagement Panel
Broader use of experts – include all different perspectives
Tours to key stakeholders, local high schools and public
External Engagement
Pro-active approach to challenging mis-information
Active Social Media Presence
Identify and engaging “Influencers”

## Slide 30
More information on www.SONGScommunity.com